## Projekttidslinje
WSC8 group 850
TIDSLINJE
0
PROJEKTOPLYSNINGER
DATO | MILEPÆL | PLACERING | UDGANGSPUNKT
2016-02-01 | Projekt start | 25 | 1
2016-02-14 | Understand key termsand concepts. | 10 | 1
2016-02-21 | Figure out why and what we want to measure. | -10 | 1
2016-03-01 | Set requrments for the measurements. | 20 | 1
2016-03-03 | Start introduction of the report | 10 | 1
2016-03-10 | Do a first trial measuremet | -15 | 1
2016-03-17 | How to preesnt the measuremetns in the report | 15 | 1
2016-03-28 | Find out what theroys we want to present in the report | -15 | 1
2016-04-24 | Finnish the measurements campaign | 15 | 1
2016-05-15 | Write report of meassured data | -20 | 1
2016-05-22 | Finelize report | 20 | 1
2016-05-23 | Praticse for the examination | -15 | 1
31.06.2016 | Exam | 15 | 1
Tip til projekttidslinje:
Positionsværdierne i projektoplysningstabellen bruges til at forhindre, at milepælsnavne overlapper hinanden på tidslinjen. Brug positiv tale til at placere navne oven over tidslinjen og negative tal til at placere dem nedenunder.
Hvis du vil tilføje flere milepæle, skal du enten indsætte nye rækker i tabellen eller begynde at skrive under den sidste post, hvorefter tabellen automatisk udvides til at omfatte de tal, du netop har tilføjet.