## Sheet1
Subjekt | Week 8 |  | Week 9 |  | Week 10 |  | Week 11 |  | Week 12 |  | Week 13 |  | Week 14 |  | Week 15 |  | Week 16 |  | Week 17 |  | Week 18 |  | Week 19 |  | Week 20 |  | Week 21 |  | Week 22
| 2017-02-20 | 2017-02-25 | 2017-02-27 | 2017-03-04 | 2017-03-06 | 2017-03-11 | 2017-03-13 | 2017-03-18 | 2017-03-20 | 2017-03-25 | 2017-03-27 | 2017-04-01 | 2017-04-03 | 2017-04-08 | 2017-04-10 | 2017-04-15 | 2017-04-17 | 2017-04-22 | 2017-04-24 | 2017-04-29 | 2017-05-01 | 2017-05-06 | 2017-05-08 | 2017-05-13 | 2017-05-15 | 2017-05-20 | 2017-05-22 | 2017-05-27 | 2017-05-29 | 2017-06-03
Write:
Motivation | bar: 2017-02-20 to 2017-02-25
Dynamic range | bar: 2017-02-20 to 2017-03-04
Rayleigh fading | bar: 2017-02-27 to 2017-03-11
Statistics | bar: 2017-02-27 to 2017-03-11
Block diagram analyse | bar: 2017-02-20 to 2017-03-11
Test setup | bar: 2017-03-13 to 2017-04-08
Measurement Campaign | bar: 2017-03-27 to 2017-04-08
Results and analysing | bar: 2017-04-03 to 2017-05-13
Discussion and Conclusion | bar: 2017-05-01 to 2017-05-20
Test setup:
Research of equipment | bar: 2017-03-13 to 2017-04-08
Assembling of setup | bar: 2017-03-27 to 2017-04-22
Initial testing | bar: 2017-04-03 to 2017-04-29
Final tests | bar: 2017-04-24 to 2017-05-13

## Sheet2
| Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21
Task | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Correction of Part 1 | bar: Week 17 M to Week 17 S
Measurement journal | bar: Week 17 M to Week 18 S
Plan measurement setup | bar: Week 17 M to Week 18 W
Setup measurement | bar: Week 18 W to Week 18 F
Measurement campaign | bar: Week 18 W to Week 19 T
Data analysing | bar: Week 17 S to Week 19 F
Finish part 2 | bar: Week 18 W to Week 19 S
Correction of whole report | bar: Week 20 M to Week 20 S